## Sheet1
ID | Module | Feature | Description | Version | Priority | Screen | Notes
AUTH-001 | Authentication | User Registration | Allow user to sign up using email and password | V1 | P0 | Register Screen | Email/password only
AUTH-002 | Authentication | User Login | Allow existing user to log in | V1 | P0 | Login Screen | Persistent session required
AUTH-003 | Authentication | Forgot Password | Allow user to reset password | V1 | P0 | Forgot Password Screen | Via email reset
AUTH-004 | Authentication | Logout | Allow user to log out from app | V1 | P0 | Settings Screen | Clear local session
AUTH-005 | Authentication | Session Persistence | Keep user logged in across app restarts | V1 | P0 | App-level | Secure token storage
BIZ-001 | Business Profile | Create Business Profile | User can set up profile used in quotation/invoice PDFs | V1 | P0 | Onboarding / Settings | Required before export
BIZ-002 | Business Profile | Edit Business Profile | User can edit business details | V1 | P0 | Settings
BIZ-003 | Business Profile | Upload Logo | User can upload logo for document branding | V1 | P1 | Settings | Optional
BIZ-004 | Business Profile | Default Payment Instructions | Set default payment instructions for invoices | V1 | P1 | Settings | Example: bank transfer details
BIZ-005 | Business Profile | Default Notes | Set default notes used in quotation/invoice | V1 | P1 | Settings
BIZ-006 | Business Profile | Numbering Prefixes | Set quotation prefix and invoice prefix | V1 | P1 | Settings | Example: Q-, INV-
BIZ-007 | Business Profile | Currency Setting | Set default currency | V1 | P0 | Settings | MYR only in V1
BIZ-008 | Business Profile | Custom Numbering Format | Support custom numbering format | V2 | P1 | Settings | Example: INV-2026-001
CUS-001 | Customers | Create Customer | Add a new customer | V1 | P0 | Customer Form
CUS-002 | Customers | Edit Customer | Edit customer details | V1 | P0 | Customer Form
CUS-003 | Customers | Delete/Archive Customer | Remove or archive customer | V1 | P1 | Customer Detail | Prefer archive if linked records exist
CUS-004 | Customers | Customer List | Show all customers | V1 | P0 | Customer List
CUS-005 | Customers | Search Customers | Search by name/company/phone | V1 | P1 | Customer List
CUS-006 | Customers | Customer Detail View | Show customer info and related documents | V1 | P1 | Customer Detail
CUS-007 | Customers | Open WhatsApp Chat | Open customer WhatsApp chat | V1 | P1 | Customer Detail | If phone exists
CUS-008 | Customers | Customer History Summary | Show customer total invoices/unpaid amounts | V2 | P1 | Customer Detail
CUS-009 | Customers | Archive/Restore Customer | Archive and restore customer records | V2 | P1 | Customer Detail / Archive
QTN-001 | Quotations | Create Quotation | Create a new quotation | V1 | P0 | Quotation Form
QTN-002 | Quotations | Edit Quotation | Edit existing quotation | V1 | P0 | Quotation Form
QTN-003 | Quotations | Save Draft Quotation | Save incomplete quotation as draft | V1 | P1 | Quotation Form
QTN-004 | Quotations | Quotation List | Show all quotations | V1 | P0 | Quotation List
QTN-005 | Quotations | Quotation Detail | Show quotation details and actions | V1 | P0 | Quotation Detail
QTN-006 | Quotations | Quotation Number Auto-Generation | Auto-generate quotation number | V1 | P0 | Quotation Form
QTN-007 | Quotations | Manual Number Edit | User may override generated number | V1 | P1 | Quotation Form
QTN-008 | Quotations | Quotation Status | Support Draft/Sent/Accepted/Rejected/Expired | V1 | P0 | Quotation Detail/List
QTN-009 | Quotations | Duplicate Quotation | Duplicate an existing quotation | V1 | P1 | Quotation Detail | Helpful for repeat jobs
QTN-010 | Quotations | Convert to Invoice | Convert quotation into invoice | V1 | P0 | Quotation Detail
QTN-011 | Quotations | Quotation Search | Search by number/customer | V1 | P1 | Quotation List
QTN-012 | Quotations | Quotation Filter | Filter by status/date | V1 | P1 | Quotation List
QTN-013 | Quotations | Export Quotation PDF | Generate quotation PDF | V1 | P0 | Quotation Detail
QTN-014 | Quotations | Share Quotation | Share quotation PDF via system share | V1 | P0 | Quotation Detail
QTN-015 | Quotations | WhatsApp Share Quotation | Share quotation through WhatsApp flow | V1 | P1 | Quotation Detail
QTN-016 | Quotations | Quotation Activity Timeline | Show activity timeline | V2 | P2 | Quotation Detail | Created/edited/shared etc.
INV-001 | Invoices | Create Invoice | Create a new invoice | V1 | P0 | Invoice Form
INV-002 | Invoices | Edit Invoice | Edit existing invoice | V1 | P0 | Invoice Form
INV-003 | Invoices | Save Draft Invoice | Save incomplete invoice as draft | V1 | P1 | Invoice Form
INV-004 | Invoices | Invoice List | Show all invoices | V1 | P0 | Invoice List
INV-005 | Invoices | Invoice Detail | Show invoice details and actions | V1 | P0 | Invoice Detail
INV-006 | Invoices | Invoice Number Auto-Generation | Auto-generate invoice number | V1 | P0 | Invoice Form
INV-007 | Invoices | Manual Number Edit | User may override generated invoice number | V1 | P1 | Invoice Form
INV-008 | Invoices | Invoice Status | Support Draft/Sent/Due Soon/Overdue/Partially Paid/Paid | V1 | P0 | Invoice Detail/List
INV-009 | Invoices | Duplicate Invoice | Duplicate an existing invoice | V1 | P1 | Invoice Detail
INV-010 | Invoices | Create Invoice from Quotation | Generate invoice from quotation | V1 | P0 | Quotation Detail
INV-011 | Invoices | Invoice Search | Search by invoice number/customer | V1 | P1 | Invoice List
INV-012 | Invoices | Invoice Filter | Filter by status/date/due state | V1 | P1 | Invoice List
INV-013 | Invoices | Export Invoice PDF | Generate invoice PDF | V1 | P0 | Invoice Detail
INV-014 | Invoices | Share Invoice | Share invoice PDF via system share | V1 | P0 | Invoice Detail
INV-015 | Invoices | WhatsApp Share Invoice | Share invoice through WhatsApp flow | V1 | P1 | Invoice Detail
INV-016 | Invoices | Invoice Activity Timeline | Show activity timeline | V2 | P2 | Invoice Detail
INV-017 | Invoices | Archive/Restore Invoice | Archive and restore invoice | V2 | P1 | Invoice Detail / Archive
PAY-001 | Payments | Mark Invoice as Paid | Mark invoice as fully paid | V1 | P0 | Invoice Detail
PAY-002 | Payments | Mark Invoice as Partially Paid | Mark invoice as partially paid | V1 | P0 | Invoice Detail
PAY-003 | Payments | Record Payment Date | Store date of payment | V1 | P0 | Payment Dialog/Form
PAY-004 | Payments | Record Payment Amount | Store payment amount | V1 | P0 | Payment Dialog/Form
PAY-005 | Payments | Record Payment Note/Reference | Store optional payment note | V1 | P1 | Payment Dialog/Form
PAY-006 | Payments | Outstanding Balance Calculation | Show remaining unpaid balance | V1 | P0 | Invoice Detail/List
PAY-007 | Payments | Payment History | Show all recorded payments for invoice | V2 | P1 | Invoice Detail
PAY-008 | Payments | Export Payment Data | Export payment records to CSV/Excel | V2 | P1 | Settings / Export
REM-001 | Reminders | Due Soon Reminder | Show invoices due soon | V1 | P0 | Home / Invoice List
REM-002 | Reminders | Overdue Reminder | Show overdue invoices | V1 | P0 | Home / Invoice List
REM-003 | Reminders | Local Notifications | Trigger local reminders based on due date | V1 | P0 | App-level
REM-004 | Reminders | Reminder Message Template | Predefined reminder text for customer follow-up | V1 | P1 | Invoice Detail
REM-005 | Reminders | Copy Reminder Message | Copy reminder message to clipboard | V1 | P1 | Invoice Detail / Reminders
REM-006 | Reminders | Reminder Quick Actions | Open invoice/share/open WhatsApp from reminder item | V1 | P1 | Home / Reminders
REM-007 | Reminders | Custom Reminder Schedule | User-defined reminder days | V2 | P1 | Settings
REM-008 | Reminders | Reminder History Log | Track reminder actions | V2 | P2 | Invoice Detail
REM-009 | Reminders | Snooze Reminder | Allow user to snooze a reminder | V2 | P2 | Reminder Item
HOME-001 | Dashboard | Home Summary Cards | Show unpaid, overdue, due this week, drafts | V1 | P0 | Home
HOME-002 | Dashboard | Recent Quotations | Show recent quotations | V1 | P1 | Home
HOME-003 | Dashboard | Recent Invoices | Show recent invoices | V1 | P1 | Home
HOME-004 | Dashboard | Quick Actions | Fast entry points to customer/quotation/invoice creation | V1 | P0 | Home
HOME-005 | Dashboard | Monthly Insights | Show monthly invoiced/collected totals | V2 | P1 | Home
HOME-006 | Dashboard | Top Customers | Show top customers by amount | V2 | P2 | Home
PDF-001 | PDF Export | Quotation PDF Template | Professional quotation PDF layout | V1 | P0 | Quotation Detail
PDF-002 | PDF Export | Invoice PDF Template | Professional invoice PDF layout | V1 | P0 | Invoice Detail
PDF-003 | PDF Export | Include Logo | Show user logo in PDF | V1 | P1 | PDF output
PDF-004 | PDF Export | Include Notes and Payment Instructions | Include extra text fields in PDF | V1 | P0 | PDF output
PDF-005 | PDF Export | Multiple PDF Templates | Offer template choices | V2 | P1 | Settings / Export
PDF-006 | PDF Export | Accent Color Selection | Let user customize document color | V2 | P2 | Settings
SHR-001 | Sharing | System Share Sheet | Share PDF via device share sheet | V1 | P0 | Quotation Detail / Invoice Detail
SHR-002 | Sharing | Share via WhatsApp | Share document using WhatsApp flow | V1 | P1 | Quotation Detail / Invoice Detail
SHR-003 | Sharing | Open WhatsApp Chat | Open WhatsApp chat with customer | V1 | P1 | Customer Detail / Invoice Detail
SHR-004 | Sharing | Copy Quotation Message | Copy quotation share text | V1 | P1 | Quotation Detail
SHR-005 | Sharing | Copy Invoice Message | Copy invoice share text | V1 | P1 | Invoice Detail
SHR-006 | Sharing | Saved Message Templates | User-defined message templates | V2 | P1 | Settings
SHR-007 | Sharing | One-Tap Reminder Share | Faster reminder-specific sharing flow | V2 | P2 | Invoice Detail / Home
SET-001 | Settings | Business Settings | Manage business profile and branding | V1 | P0 | Settings
SET-002 | Settings | Notification Settings | Manage reminder preferences | V1 | P1 | Settings
SET-003 | Settings | Prefix Settings | Configure quotation/invoice prefixes | V1 | P1 | Settings
SET-004 | Settings | Default Notes Settings | Configure default note fields | V1 | P1 | Settings
SET-005 | Settings | Default Reminder Settings | Configure default reminder timing | V1 | P1 | Settings
SET-006 | Settings | Export Data | Export data to CSV/Excel | V2 | P1 | Settings
SET-007 | Settings | Archive Manager | View archived records | V2 | P2 | Settings
CAT-001 | Saved Items | Saved Service/Item Catalog | Reusable line item catalog | V2 | P1 | Saved Items
CAT-002 | Saved Items | Insert Saved Item into Document | Add saved item into quotation/invoice quickly | V2 | P1 | Quotation Form / Invoice Form
CAT-003 | Saved Items | Edit Saved Item | Modify saved item entry | V2 | P1 | Saved Items
CAT-004 | Saved Items | Archive Saved Item | Archive saved catalog item | V2 | P2 | Saved Items
EXP-001 | Export | Export Customers CSV | Export customer list | V2 | P1 | Settings / Export
EXP-002 | Export | Export Invoices CSV | Export invoices list | V2 | P1 | Settings / Export
EXP-003 | Export | Export Payments CSV | Export payments list | V2 | P1 | Settings / Export
EXP-004 | Export | Export by Date Range | Export filtered records by date | V2 | P1 | Settings / Export

## Sheet2
Screen ID | Screen Name | Version | Module | Purpose | Main Actions | Related Features | Notes
AUTH-SPLASH | Splash Screen | V1 | Authentication | Check session and route user to correct screen | Check login session; Navigate to Home; Navigate to Login | AUTH-005 | Show app logo/loading state
AUTH-LOGIN | Login Screen | V1 | Authentication | Allow existing user to log in | Login; Go to Register; Go to Forgot Password | AUTH-002; AUTH-003; AUTH-005 | Email/password login
AUTH-REGISTER | Register Screen | V1 | Authentication | Allow new user to create account | Register; Go to Login | AUTH-001 | After registration, route to Initial Business Setup
AUTH-FORGOT | Forgot Password Screen | V1 | Authentication | Allow user to reset password | Submit reset email; Return to Login | AUTH-003 | Via email reset
ONB-SETUP | Initial Business Setup | V1 | Business Profile | Collect minimum business profile information after first sign-up | Save business profile; Continue to Home | BIZ-001; BIZ-004; BIZ-005; BIZ-006; BIZ-007 | Recommended after first registration
HOME-DASHBOARD | Home Dashboard | V1 | Dashboard | Show key business overview and quick actions | Create customer; Create quotation; Create invoice; Open filtered invoice list | HOME-001; HOME-002; HOME-003; HOME-004; REM-001; REM-002 | Should focus on unpaid and overdue amounts
CUS-LIST | Customer List | V1 | Customers | Show all customers with search | Add customer; Search customer; Open customer detail | CUS-001; CUS-004; CUS-005 | Use floating action button or top action button
CUS-FORM | Create/Edit Customer | V1 | Customers | Create or update customer details | Save customer; Cancel; Archive customer | CUS-001; CUS-002; CUS-003 | Archive preferred over delete if linked records exist
CUS-DETAIL | Customer Detail | V1 | Customers | Show customer information and related documents | Edit customer; Call; Email; Open WhatsApp; Create quotation; Create invoice | CUS-006; CUS-007; QTN-001; INV-001 | Can show related quotations and invoices
QTN-LIST | Quotation List | V1 | Quotations | Show all quotations with search and filter | Create quotation; Search; Filter; Open quotation detail | QTN-004; QTN-011; QTN-012 | Status tabs can improve usability
QTN-FORM | Create/Edit Quotation | V1 | Quotations | Create or update quotation | Save draft; Save quotation; Add item; Remove item; Select customer | QTN-001; QTN-002; QTN-003; QTN-006; QTN-007 | Core form screen
QTN-DETAIL | Quotation Detail | V1 | Quotations | Show quotation details and available actions | Edit; Export PDF; Share; Share via WhatsApp; Copy message; Convert to invoice; Duplicate; Update status | QTN-005; QTN-008; QTN-009; QTN-010; QTN-013; QTN-014; QTN-015; INV-010; PDF-001; SHR-001; SHR-002; SHR-004 | Important conversion screen
INV-LIST | Invoice List | V1 | Invoices | Show invoices with search, filter, and payment status | Create invoice; Search; Filter; Open invoice detail | INV-004; INV-011; INV-012; REM-001; REM-002 | Should clearly show outstanding amount and status
INV-FORM | Create/Edit Invoice | V1 | Invoices | Create or update invoice | Save draft; Save invoice; Add item; Remove item; Select customer | INV-001; INV-002; INV-003; INV-006; INV-007 | Can be opened directly or from quotation conversion
INV-DETAIL | Invoice Detail | V1 | Invoices | Show invoice details, payment state, and follow-up actions | Edit; Export PDF; Share; Share via WhatsApp; Copy invoice message; Copy reminder message; Open WhatsApp; Mark paid; Mark partial; Duplicate | INV-005; INV-008; INV-009; INV-013; INV-014; INV-015; PAY-001; PAY-002; PAY-006; PDF-002; SHR-001; SHR-002; SHR-003; SHR-005; REM-004; REM-005 | One of the most important screens
PAY-DIALOG | Record Payment Dialog | V1 | Payments | Record full or partial payment | Enter amount; Enter date; Enter note; Save payment | PAY-001; PAY-002; PAY-003; PAY-004; PAY-005; PAY-006 | Can be modal bottom sheet or full screen
REM-VIEW | Reminder / Due Monitoring View | V1 | Reminders | Show invoices requiring follow-up | Open invoice; Copy reminder message; Share invoice; Open WhatsApp | REM-001; REM-002; REM-004; REM-005; REM-006 | Can be a Home section first instead of separate tab
PDF-PREVIEW | PDF Preview | V1 | PDF Export | Preview generated PDF before sharing | Preview; Save; Share; Share via WhatsApp | PDF-001; PDF-002; PDF-003; PDF-004; SHR-001; SHR-002 | Optional for V1 but improves confidence
SET-MAIN | Settings Main | V1 | Settings | Show all configurable settings | Open business settings; Open numbering settings; Open reminder settings; Logout | SET-001; SET-002; SET-003; SET-004; SET-005; AUTH-004 | Main settings hub
SET-BIZ | Business Profile Settings | V1 | Business Profile | Manage business profile and branding | Edit business info; Upload logo; Save | BIZ-002; BIZ-003; BIZ-004; BIZ-005; BIZ-007; SET-001 | Used for PDF sender information
SET-NUM | Numbering Settings | V1 | Settings | Manage quotation and invoice numbering | Edit quotation prefix; Edit invoice prefix; Save | BIZ-006; SET-003 | Custom format can be V2
SET-REM | Reminder Settings | V1 | Reminders | Manage default reminder preferences | Set days before due; Toggle due date reminder; Set days after due; Save | REM-003; SET-002; SET-005 | Custom schedule can be expanded in V2
SET-NOTES | Default Notes Settings | V1 | Settings | Manage default notes and payment instructions | Edit default quotation note; Edit default invoice note; Edit payment instructions; Save | BIZ-004; BIZ-005; SET-004 | Optional separate screen, or combine with Business Profile Settings
CAT-LIST | Saved Items Catalog | V2 | Saved Items | Manage reusable service/item catalog | Add item; Edit item; Archive item | CAT-001; CAT-003; CAT-004 | Useful for reducing repeated input
CAT-FORM | Create/Edit Saved Item | V2 | Saved Items | Create or update reusable item/service | Save item; Cancel | CAT-001; CAT-003 | Fields: name, description, default unit price
EXP-MAIN | Data Export Screen | V2 | Export | Export business data | Export customers; Export invoices; Export payments; Choose date range | EXP-001; EXP-002; EXP-003; EXP-004; SET-006 | CSV/Excel export
ARC-MAIN | Archive Manager | V2 | Settings | View and restore archived records | View archived customers; View archived quotations; View archived invoices; Restore record | CUS-009; INV-017; SET-007 | Can be under Settings
PDF-TEMPLATE | PDF Template Settings | V2 | PDF Export | Choose and customize PDF templates | Select template; Choose accent color; Save | PDF-005; PDF-006 | Improves branding and perceived value
SHR-TEMPLATE | Message Template Settings | V2 | Sharing | Manage custom sharing and reminder messages | Edit quotation message; Edit invoice message; Edit reminder message; Save | SHR-006; SHR-007 | Supports user-defined templates
INSIGHTS | Insights Dashboard | V2 | Dashboard | Show monthly business summary and top customers | View monthly invoiced total; View collected total; View top customers | HOME-005; HOME-006; CUS-008 | Keep lightweight, not accounting-heavy
ACTIVITY-TIMELINE | Activity Timeline | V2 | Quotations / Invoices | Show document activity history | View created/edited/shared/payment events | QTN-016; INV-016; REM-008 | Can be embedded inside detail screens

## Sheet3
Table | Field | Type | Required | Default / Example | Foreign Key | Index / Unique | Description | Version
auth.users | id | uuid | Yes | Generated by Supabase Auth |  | Primary Key | Supabase built-in user table | V1
business_profiles | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Business profile ID | V1
business_profiles | user_id | uuid | Yes | auth.uid() | auth.users(id) | Unique | Owner of this business profile | V1
business_profiles | business_name | text | Yes | Example: Eric Design Studio |  |  | Business or personal display name used in PDFs | V1
business_profiles | phone | text | No | 60123456789 |  |  | Business phone number | V1
business_profiles | email | text | No | user@example.com |  |  | Business email displayed on documents | V1
business_profiles | address | text | No | Business address |  |  | Business address displayed on documents | V1
business_profiles | logo_url | text | No | Supabase Storage URL |  |  | Logo file URL | V1
business_profiles | currency | text | Yes | MYR |  |  | Default currency; V1 should use MYR | V1
business_profiles | payment_instructions | text | No | Bank account / DuitNow details |  |  | Default payment instructions for invoices | V1
business_profiles | default_quotation_notes | text | No | Thank you for your inquiry. |  |  | Default notes for quotations | V1
business_profiles | default_invoice_notes | text | No | Thank you for your business. |  |  | Default notes for invoices | V1
business_profiles | quotation_prefix | text | Yes | Q- |  |  | Default quotation prefix | V1
business_profiles | invoice_prefix | text | Yes | INV- |  |  | Default invoice prefix | V1
business_profiles | quotation_next_number | int | Yes | 1 |  |  | Next quotation running number | V1
business_profiles | invoice_next_number | int | Yes | 1 |  |  | Next invoice running number | V1
business_profiles | timezone | text | Yes | Asia/Kuala_Lumpur |  |  | User/business timezone for reminders | V1
business_profiles | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
business_profiles | updated_at | timestamptz | Yes | now() |  |  | Last update timestamp | V1
customers | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Customer ID | V1
customers | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this customer | V1
customers | name | text | Yes | John Tan |  |  | Customer name | V1
customers | company_name | text | No | ABC Sdn Bhd |  |  | Customer company name | V1
customers | phone | text | No | 60123456789 |  |  | Customer phone number | V1
customers | whatsapp_number | text | No | 60123456789 |  |  | WhatsApp number if different from phone | V1
customers | email | text | No | customer@example.com |  |  | Customer email | V1
customers | billing_address | text | No | Customer address |  |  | Customer billing address | V1
customers | notes | text | No | Internal notes |  |  | Private customer notes | V1
customers | is_archived | boolean | Yes | FALSE |  | Index | Archive flag instead of hard delete | V1
customers | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
customers | updated_at | timestamptz | Yes | now() |  |  | Last update timestamp | V1
quotations | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Quotation ID | V1
quotations | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this quotation | V1
quotations | customer_id | uuid | Yes |  | customers(id) | Index | Linked customer | V1
quotations | quotation_number | text | Yes | Q-2026-001 |  | Unique per user | Quotation document number | V1
quotations | issue_date | date | Yes | 2026-04-25 |  |  | Quotation issue date | V1
quotations | valid_until | date | No | 2026-05-25 |  |  | Quotation validity date | V1
quotations | currency | text | Yes | MYR |  |  | Document currency | V1
quotations | subtotal | numeric(12,2) | Yes | 0 |  |  | Subtotal before discount | V1
quotations | discount_amount | numeric(12,2) | Yes | 0 |  |  | Fixed discount amount | V1
quotations | total_amount | numeric(12,2) | Yes | 0 |  |  | Final total amount | V1
quotations | notes | text | No | Quotation notes |  |  | Notes shown on quotation PDF | V1
quotations | payment_instructions | text | No | Optional payment instructions |  |  | Optional payment information | V1
quotations | status | text | Yes | draft |  | Index | Draft, sent, accepted, rejected, expired | V1
quotations | converted_invoice_id | uuid | No |  | invoices(id) | Index | Invoice created from this quotation | V1
quotations | is_archived | boolean | Yes | FALSE |  | Index | Archive flag | V2
quotations | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
quotations | updated_at | timestamptz | Yes | now() |  |  | Last update timestamp | V1
quotation_items | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Quotation item ID | V1
quotation_items | quotation_id | uuid | Yes |  | quotations(id) | Index | Parent quotation | V1
quotation_items | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this item | V1
quotation_items | item_name | text | Yes | Website Design |  |  | Item/service name | V1
quotation_items | description | text | No | Landing page design |  |  | Optional item description | V1
quotation_items | quantity | numeric(12,2) | Yes | 1 |  |  | Item quantity | V1
quotation_items | unit_price | numeric(12,2) | Yes | 500 |  |  | Price per unit | V1
quotation_items | line_total | numeric(12,2) | Yes | 500 |  |  | quantity * unit_price | V1
quotation_items | sort_order | int | Yes | 0 |  |  | Display order in PDF/form | V1
quotation_items | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
invoices | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Invoice ID | V1
invoices | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this invoice | V1
invoices | customer_id | uuid | Yes |  | customers(id) | Index | Linked customer | V1
invoices | source_quotation_id | uuid | No |  | quotations(id) | Index | Original quotation if created from quotation | V1
invoices | invoice_number | text | Yes | INV-2026-001 |  | Unique per user | Invoice document number | V1
invoices | issue_date | date | Yes | 2026-04-25 |  |  | Invoice issue date | V1
invoices | due_date | date | Yes | 2026-05-25 |  | Index | Payment due date | V1
invoices | currency | text | Yes | MYR |  |  | Document currency | V1
invoices | subtotal | numeric(12,2) | Yes | 0 |  |  | Subtotal before discount | V1
invoices | discount_amount | numeric(12,2) | Yes | 0 |  |  | Fixed discount amount | V1
invoices | total_amount | numeric(12,2) | Yes | 0 |  |  | Final invoice amount | V1
invoices | amount_paid | numeric(12,2) | Yes | 0 |  |  | Total recorded payment amount | V1
invoices | balance_due | numeric(12,2) | Yes | 0 |  | Index | Outstanding balance | V1
invoices | notes | text | No | Invoice notes |  |  | Notes shown on invoice PDF | V1
invoices | payment_instructions | text | No | Bank account / DuitNow details |  |  | Payment instructions shown on invoice PDF | V1
invoices | status | text | Yes | draft |  | Index | Draft, sent, partially_paid, paid, cancelled | V1
invoices | is_archived | boolean | Yes | FALSE |  | Index | Archive flag | V2
invoices | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
invoices | updated_at | timestamptz | Yes | now() |  |  | Last update timestamp | V1
invoice_items | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Invoice item ID | V1
invoice_items | invoice_id | uuid | Yes |  | invoices(id) | Index | Parent invoice | V1
invoice_items | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this item | V1
invoice_items | item_name | text | Yes | Website Design |  |  | Item/service name | V1
invoice_items | description | text | No | Landing page design |  |  | Optional item description | V1
invoice_items | quantity | numeric(12,2) | Yes | 1 |  |  | Item quantity | V1
invoice_items | unit_price | numeric(12,2) | Yes | 500 |  |  | Price per unit | V1
invoice_items | line_total | numeric(12,2) | Yes | 500 |  |  | quantity * unit_price | V1
invoice_items | sort_order | int | Yes | 0 |  |  | Display order in PDF/form | V1
invoice_items | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
payments | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Payment ID | V1
payments | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this payment | V1
payments | invoice_id | uuid | Yes |  | invoices(id) | Index | Linked invoice | V1
payments | amount | numeric(12,2) | Yes | 100 |  |  | Payment amount | V1
payments | payment_date | date | Yes | 2026-04-25 |  |  | Date payment was received | V1
payments | payment_method | text | No | Bank Transfer |  |  | Optional payment method | V1
payments | reference_note | text | No | Transaction ID / note |  |  | Optional payment reference | V1
payments | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
reminder_settings | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Reminder setting ID | V1
reminder_settings | user_id | uuid | Yes | auth.uid() | auth.users(id) | Unique | Owner of reminder settings | V1
reminder_settings | remind_before_days | int | Yes | 3 |  |  | Send reminder X days before due date | V1
reminder_settings | remind_on_due_date | boolean | Yes | TRUE |  |  | Send reminder on due date | V1
reminder_settings | remind_after_days | int | Yes | 3 |  |  | Send reminder X days after due date | V1
reminder_settings | enable_push_notifications | boolean | Yes | TRUE |  |  | Enable FCM push reminders | V1
reminder_settings | enable_local_notifications | boolean | Yes | TRUE |  |  | Enable local notifications if used | V1
reminder_settings | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
reminder_settings | updated_at | timestamptz | Yes | now() |  |  | Last update timestamp | V1
user_devices | id | uuid | Yes | gen_random_uuid() |  | Primary Key | User device ID | V1
user_devices | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this device token | V1
user_devices | fcm_token | text | Yes | FCM token |  | Unique | FCM device token | V1
user_devices | platform | text | Yes | android |  |  | android, ios, web | V1
user_devices | device_name | text | No | Samsung A55 |  |  | Optional device name | V1
user_devices | is_active | boolean | Yes | TRUE |  | Index | Inactive if token becomes invalid | V1
user_devices | last_seen_at | timestamptz | Yes | now() |  |  | Last time app updated this token | V1
user_devices | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
user_devices | updated_at | timestamptz | Yes | now() |  |  | Last update timestamp | V1
reminder_logs | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Reminder log ID | V1
reminder_logs | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of this reminder log | V1
reminder_logs | invoice_id | uuid | Yes |  | invoices(id) | Index | Linked invoice | V1
reminder_logs | reminder_type | text | Yes | before_due |  |  | before_due, due_today, after_due, overdue | V1
reminder_logs | channel | text | Yes | fcm |  |  | fcm, local, email, manual | V1
reminder_logs | status | text | Yes | sent |  |  | pending, sent, failed, skipped | V1
reminder_logs | sent_at | timestamptz | No | now() |  |  | When reminder was sent | V1
reminder_logs | error_message | text | No | Error detail |  |  | Error message if failed | V1
reminder_logs | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V1
saved_items | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Saved item ID | V2
saved_items | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of saved item | V2
saved_items | item_name | text | Yes | Website Design |  |  | Reusable item/service name | V2
saved_items | description | text | No | Landing page design |  |  | Reusable default description | V2
saved_items | unit_price | numeric(12,2) | Yes | 500 |  |  | Reusable default price | V2
saved_items | is_archived | boolean | Yes | FALSE |  | Index | Archive flag | V2
saved_items | created_at | timestamptz | Yes | now() |  |  | Record creation timestamp | V2
saved_items | updated_at | timestamptz | Yes | now() |  |  | Last update timestamp | V2
document_activity_logs | id | uuid | Yes | gen_random_uuid() |  | Primary Key | Activity log ID | V2
document_activity_logs | user_id | uuid | Yes | auth.uid() | auth.users(id) | Index | Owner of activity log | V2
document_activity_logs | document_type | text | Yes | invoice |  |  | invoice or quotation | V2
document_activity_logs | document_id | uuid | Yes | invoice_id or quotation_id |  | Index | Related document ID | V2
document_activity_logs | action | text | Yes | shared |  |  | created, updated, shared, paid, status_changed | V2
document_activity_logs | metadata | jsonb | No | {} |  |  | Extra activity details | V2
document_activity_logs | created_at | timestamptz | Yes | now() |  |  | Activity timestamp | V2

## Sheet4
Entity | Status / State | Type | Description | Trigger / Rule | Can User Set Manually? | Used In Screen | Version | Notes
Quotation | draft | Status | Quotation is created but not yet sent | Default status when user saves as draft | Yes | Quotation List; Quotation Detail | V1 | User can still edit freely
Quotation | sent | Status | Quotation has been sent to customer | User taps Mark as Sent or shares quotation | Yes | Quotation List; Quotation Detail | V1 | Sharing can optionally auto-set to sent
Quotation | accepted | Status | Customer accepted the quotation | User taps Mark as Accepted | Yes | Quotation Detail | V1 | Accepted quotation can be converted to invoice
Quotation | rejected | Status | Customer rejected the quotation | User taps Mark as Rejected | Yes | Quotation Detail | V1 | Rejected quotation should not be converted by default
Quotation | expired | Computed State | Quotation validity date has passed | valid_until < today AND status not in accepted/rejected | No | Quotation List; Quotation Detail | V1 | Better as computed state, not permanent status
Quotation | archived | Archive State | Quotation hidden from normal list | is_archived = true | Yes | Archive Manager | V2 | Do not hard delete if linked to invoice
Invoice | draft | Status | Invoice is created but not finalized | Default status when user saves as draft | Yes | Invoice List; Invoice Detail | V1 | Draft invoice should not trigger reminders
Invoice | sent | Status | Invoice has been issued/sent to customer | User taps Mark as Sent or shares invoice | Yes | Invoice List; Invoice Detail | V1 | Sent invoice can trigger reminders
Invoice | partially_paid | Status | Invoice has received some payment but not fully paid | total paid > 0 AND total paid < total_amount | Auto | Invoice List; Invoice Detail | V1 | Should be derived after payment save
Invoice | paid | Status | Invoice is fully paid | total paid >= total_amount | Auto | Invoice List; Invoice Detail | V1 | Reminders should stop
Invoice | cancelled | Status | Invoice is cancelled | User taps Cancel Invoice | Yes | Invoice Detail | V2 | Optional for V1; useful later
Invoice | archived | Archive State | Invoice hidden from normal list | is_archived = true | Yes | Archive Manager | V2 | Archived invoice still kept in database
Invoice | due_soon | Due State | Invoice is close to due date | balance_due > 0 AND due_date > today AND due_date <= today + reminder_settings.remind_before_days | No | Home; Invoice List; Reminder View | V1 | Computed state, not stored status
Invoice | due_today | Due State | Invoice is due today | balance_due > 0 AND due_date = today | No | Home; Invoice List; Reminder View | V1 | Computed state, not stored status
Invoice | overdue | Due State | Invoice due date has passed and still unpaid | balance_due > 0 AND due_date < today | No | Home; Invoice List; Reminder View | V1 | Computed state, not stored status
Invoice | not_due | Due State | Invoice is not due yet and not within due soon window | balance_due > 0 AND due_date > today + reminder_settings.remind_before_days | No | Invoice List | V1 | Normal unpaid future invoice
Payment | recorded | Status | Payment has been saved | User records payment amount/date | Auto | Invoice Detail; Payment History | V1 | Each payment record should not be edited casually after creation
Payment | voided | Status | Payment was voided/reversed | User voids payment record | Yes | Payment History | V2 | Optional; do not hard delete payment in mature version
Payment | full_payment | Payment State | Payment settles invoice total | total paid >= total_amount | Auto | Invoice Detail | V1 | Updates invoice status to paid
Payment | partial_payment | Payment State | Payment only settles part of invoice | total paid > 0 AND total paid < total_amount | Auto | Invoice Detail | V1 | Updates invoice status to partially_paid
Reminder | pending | Status | Reminder is scheduled or eligible but not sent | Reminder due but processing not completed | Auto | Reminder Logs; Background Job | V2 | For V1, may not need pending logs
Reminder | sent | Status | Reminder notification was sent successfully | FCM/local notification success | Auto | Reminder Logs | V1 | Used to avoid duplicate reminders
Reminder | failed | Status | Reminder failed to send | FCM/API error | Auto | Reminder Logs | V1 | Store error_message
Reminder | skipped | Status | Reminder was not sent because condition changed | Invoice paid/cancelled/draft or token inactive | Auto | Reminder Logs | V2 | Optional
Reminder | before_due | Reminder Type | Reminder before invoice due date | today = due_date - remind_before_days | Auto | Reminder Logs; FCM | V1 | Send only if invoice unpaid and sent
Reminder | due_today | Reminder Type | Reminder on invoice due date | today = due_date AND remind_on_due_date = true | Auto | Reminder Logs; FCM | V1 | Send only if invoice unpaid and sent
Reminder | after_due | Reminder Type | Reminder after invoice due date | today = due_date + remind_after_days | Auto | Reminder Logs; FCM | V1 | Send only if invoice unpaid and sent
Reminder | overdue | Reminder Type | General overdue reminder | balance_due > 0 AND due_date < today | Auto | Reminder View | V1 | Can be displayed continuously, but notifications should avoid duplicates
Customer | active | State | Customer appears in normal customer list | is_archived = false | Auto | Customer List | V1 | Default state
Customer | archived | State | Customer hidden from normal customer list | is_archived = true | Yes | Archive Manager | V1/V2 | Prefer archive over hard delete if customer has documents
Saved Item | active | State | Saved item appears in item catalog | is_archived = false | Auto | Saved Items | V2 | Default state
Saved Item | archived | State | Saved item hidden from normal catalog | is_archived = true | Yes | Saved Items; Archive Manager | V2 | Do not affect existing invoice/quotation items
User Device | active | State | FCM token is active | is_active = true | Auto | App-level; Edge Function | V1 | Used for push notifications
User Device | inactive | State | FCM token is invalid or user logged out | is_active = false | Auto | App-level; Edge Function | V1 | Set inactive after FCM invalid token response or logout
Business Profile | incomplete | State | Profile missing required information | business_name is null/empty | No | Onboarding; Settings | V1 | Should block final PDF export or show warning
Business Profile | complete | State | Profile has minimum required fields | business_name exists | No | Onboarding; Settings | V1 | More fields optional

## Sheet5
Sprint | Task ID | Phase | Module | Task | Related Feature IDs | Priority | Estimated Effort | Dependencies | Status | Notes
Sprint 0 | SETUP-001 | Project Setup | Project Setup | Create Flutter project structure |  | P0 | 0.5 day |  | Not Started | Use feature-first folder structure
Sprint 0 | SETUP-002 | Project Setup | Project Setup | Setup Git repository and branching strategy |  | P0 | 0.5 day | SETUP-001 | Not Started | Use main/dev branches
Sprint 0 | SETUP-003 | Project Setup | Project Setup | Setup Flutter environment for Android |  | P0 | 0.5 day | SETUP-001 | Not Started | iOS can be added later if needed
Sprint 0 | SETUP-004 | Project Setup | Project Setup | Add base Flutter packages |  | P0 | 0.5 day | SETUP-001 | Not Started | Riverpod/go_router/supabase_flutter/intl/pdf/share_plus etc.
Sprint 0 | SETUP-005 | Project Setup | Project Setup | Setup app theme and design system |  | P1 | 1 day | SETUP-001 | Not Started | Colors, typography, spacing, buttons, cards
Sprint 0 | SETUP-006 | Project Setup | Supabase | Create Supabase project |  | P0 | 0.5 day |  | Not Started | Create dev project first
Sprint 0 | SETUP-007 | Project Setup | Supabase | Configure Supabase Auth | AUTH-001; AUTH-002; AUTH-003 | P0 | 0.5 day | SETUP-006 | Not Started | Email/password auth
Sprint 0 | SETUP-008 | Project Setup | Supabase | Prepare initial database migration files |  | P0 | 1 day | SETUP-006 | Not Started | Use SQL migration files
Sprint 0 | SETUP-009 | Project Setup | Supabase | Setup Row Level Security strategy |  | P0 | 1 day | SETUP-008 | Not Started | Required before production
Sprint 0 | SETUP-010 | Project Setup | Architecture | Create repository interfaces |  | P0 | 1 day | SETUP-001 | Not Started | AuthRepository, CustomerRepository, InvoiceRepository, etc.
Sprint 0 | SETUP-011 | Project Setup | Architecture | Create base error/result handling |  | P1 | 0.5 day | SETUP-010 | Not Started | Useful for clean app-wide error handling
Sprint 0 | SETUP-012 | Project Setup | Architecture | Setup app routing structure |  | P0 | 0.5 day | SETUP-004 | Not Started | Use go_router
Sprint 0 | SETUP-013 | Project Setup | Architecture | Setup environment configuration |  | P0 | 0.5 day | SETUP-006 | Not Started | Dev/prod Supabase URL and anon key
Sprint 0 | SETUP-014 | Project Setup | QA | Setup basic logging and debug tools |  | P1 | 0.5 day | SETUP-001 | Not Started | Sentry can be added later
Sprint 0 | SETUP-015 | Project Setup | QA | Create development checklist |  | P1 | 0.5 day |  | Not Started | Manual QA checklist per screen
Sprint 1 | AUTH-DEV-001 | Foundation | Authentication | Build Splash Screen | AUTH-005 | P0 | 0.5 day | SETUP-012 | Not Started | Check current session
Sprint 1 | AUTH-DEV-002 | Foundation | Authentication | Build Login Screen | AUTH-002 | P0 | 1 day | AUTH-DEV-001 | Not Started | Email/password login
Sprint 1 | AUTH-DEV-003 | Foundation | Authentication | Build Register Screen | AUTH-001 | P0 | 1 day | AUTH-DEV-002 | Not Started | After register go to onboarding
Sprint 1 | AUTH-DEV-004 | Foundation | Authentication | Build Forgot Password Screen | AUTH-003 | P0 | 0.5 day | AUTH-DEV-002 | Not Started | Email reset flow
Sprint 1 | AUTH-DEV-005 | Foundation | Authentication | Implement AuthRepository with Supabase | AUTH-001; AUTH-002; AUTH-003; AUTH-005 | P0 | 1 day | SETUP-010; SETUP-007 | Not Started | Keep Supabase inside data layer
Sprint 1 | AUTH-DEV-006 | Foundation | Authentication | Implement logout | AUTH-004 | P0 | 0.5 day | AUTH-DEV-005 | Not Started | Logout from Settings later
Sprint 1 | DB-DEV-001 | Foundation | Database | Create business_profiles table | BIZ-001; BIZ-002 | P0 | 0.5 day | SETUP-008 | Not Started | Include numbering fields
Sprint 1 | DB-DEV-002 | Foundation | Database | Create customers table | CUS-001; CUS-002; CUS-004 | P0 | 0.5 day | SETUP-008 | Not Started | Include archive flag
Sprint 1 | DB-DEV-003 | Foundation | Database | Create quotations and quotation_items tables | QTN-001; QTN-004 | P0 | 1 day | SETUP-008 | Not Started | Include totals and status
Sprint 1 | DB-DEV-004 | Foundation | Database | Create invoices and invoice_items tables | INV-001; INV-004 | P0 | 1 day | SETUP-008 | Not Started | Include amount_paid and balance_due
Sprint 1 | DB-DEV-005 | Foundation | Database | Create payments table | PAY-001; PAY-002; PAY-003; PAY-004 | P0 | 0.5 day | SETUP-008 | Not Started | Linked to invoices
Sprint 1 | DB-DEV-006 | Foundation | Database | Create reminder_settings, user_devices, reminder_logs tables | REM-001; REM-002; REM-003 | P0 | 1 day | SETUP-008 | Not Started | Required for FCM push reminders
Sprint 1 | DB-DEV-007 | Foundation | Database | Apply RLS policies for business_profiles |  | P0 | 0.5 day | DB-DEV-001; SETUP-009 | Not Started | User can only access own profile
Sprint 1 | DB-DEV-008 | Foundation | Database | Apply RLS policies for customers |  | P0 | 0.5 day | DB-DEV-002; SETUP-009 | Not Started | User can only access own customers
Sprint 1 | DB-DEV-009 | Foundation | Database | Apply RLS policies for quotations and items |  | P0 | 0.5 day | DB-DEV-003; SETUP-009 | Not Started | User can only access own quotation data
Sprint 1 | DB-DEV-010 | Foundation | Database | Apply RLS policies for invoices, items, and payments |  | P0 | 0.5 day | DB-DEV-004; DB-DEV-005; SETUP-009 | Not Started | User can only access own invoice/payment data
Sprint 1 | DB-DEV-011 | Foundation | Database | Apply RLS policies for reminder tables |  | P0 | 0.5 day | DB-DEV-006; SETUP-009 | Not Started | Edge Function may need service role access
Sprint 1 | BIZ-DEV-001 | Foundation | Business Profile | Build Initial Business Setup screen | BIZ-001; BIZ-007 | P0 | 1 day | AUTH-DEV-005; DB-DEV-001 | Not Started | Collect minimum business info
Sprint 1 | BIZ-DEV-002 | Foundation | Business Profile | Implement BusinessProfileRepository | BIZ-001; BIZ-002 | P0 | 1 day | DB-DEV-001 | Not Started | Supabase implementation
Sprint 1 | HOME-DEV-001 | Foundation | Navigation | Create main navigation shell | HOME-004 | P0 | 1 day | AUTH-DEV-005 | Not Started | Bottom nav: Home, Customers, Quotations, Invoices, Settings
Sprint 2 | CUS-DEV-001 | Core CRUD | Customers | Build Customer List screen | CUS-004; CUS-005 | P0 | 1 day | DB-DEV-002; HOME-DEV-001 | Not Started | Search included
Sprint 2 | CUS-DEV-002 | Core CRUD | Customers | Build Create/Edit Customer form | CUS-001; CUS-002 | P0 | 1 day | CUS-DEV-001 | Not Started | Validate required fields
Sprint 2 | CUS-DEV-003 | Core CRUD | Customers | Build Customer Detail screen | CUS-006; CUS-007 | P1 | 1 day | CUS-DEV-002 | Not Started | Include quick actions
Sprint 2 | CUS-DEV-004 | Core CRUD | Customers | Implement CustomerRepository | CUS-001; CUS-002; CUS-003; CUS-004; CUS-005 | P0 | 1 day | DB-DEV-002 | Not Started | Supabase implementation
Sprint 2 | CUS-DEV-005 | Core CRUD | Customers | Implement customer archive behavior | CUS-003 | P1 | 0.5 day | CUS-DEV-004 | Not Started | Do not hard delete if linked records exist
Sprint 2 | QTN-DEV-001 | Core CRUD | Quotations | Build Quotation List screen | QTN-004; QTN-011; QTN-012 | P0 | 1 day | DB-DEV-003; HOME-DEV-001 | Not Started | List, search, filter
Sprint 2 | QTN-DEV-002 | Core CRUD | Quotations | Build Quotation Form screen | QTN-001; QTN-002; QTN-003; QTN-006; QTN-007 | P0 | 2 days | QTN-DEV-001; CUS-DEV-004 | Not Started | Customer selector and item rows
Sprint 2 | QTN-DEV-003 | Core CRUD | Quotations | Implement quotation line item editor | QTN-001 | P0 | 1 day | QTN-DEV-002 | Not Started | Add/remove/reorder items
Sprint 2 | QTN-DEV-004 | Core CRUD | Quotations | Implement quotation total calculation | QTN-001 | P0 | 0.5 day | QTN-DEV-003 | Not Started | Subtotal, discount, total
Sprint 2 | QTN-DEV-005 | Core CRUD | Quotations | Implement QuotationRepository | QTN-001; QTN-002; QTN-004; QTN-008 | P0 | 1.5 days | DB-DEV-003 | Not Started | Save quotation and items transaction-like
Sprint 2 | QTN-DEV-006 | Core CRUD | Quotations | Build Quotation Detail screen | QTN-005; QTN-008 | P0 | 1 day | QTN-DEV-005 | Not Started | Show status and actions
Sprint 2 | QTN-DEV-007 | Core CRUD | Quotations | Implement quotation duplicate | QTN-009 | P1 | 0.5 day | QTN-DEV-005 | Not Started | Helpful for repeat jobs
Sprint 2 | QTN-DEV-008 | Core CRUD | Quotations | Implement quotation status update | QTN-008 | P0 | 0.5 day | QTN-DEV-006 | Not Started | Draft, sent, accepted, rejected
Sprint 2 | INV-DEV-001 | Core CRUD | Invoices | Build Invoice List screen | INV-004; INV-011; INV-012 | P0 | 1 day | DB-DEV-004; HOME-DEV-001 | Not Started | List, search, filter
Sprint 2 | INV-DEV-002 | Core CRUD | Invoices | Build Invoice Form screen | INV-001; INV-002; INV-003; INV-006; INV-007 | P0 | 2 days | INV-DEV-001; CUS-DEV-004 | Not Started | Similar to quotation form
Sprint 2 | INV-DEV-003 | Core CRUD | Invoices | Implement invoice line item editor | INV-001 | P0 | 1 day | INV-DEV-002 | Not Started | Add/remove/reorder items
Sprint 2 | INV-DEV-004 | Core CRUD | Invoices | Implement invoice total and balance calculation | INV-001; PAY-006 | P0 | 0.5 day | INV-DEV-003 | Not Started | Subtotal, discount, total, balance_due
Sprint 2 | INV-DEV-005 | Core CRUD | Invoices | Implement InvoiceRepository | INV-001; INV-002; INV-004; INV-008 | P0 | 1.5 days | DB-DEV-004 | Not Started | Save invoice and items
Sprint 2 | INV-DEV-006 | Core CRUD | Invoices | Build Invoice Detail screen | INV-005; INV-008; PAY-006 | P0 | 1 day | INV-DEV-005 | Not Started | Show payment summary and actions
Sprint 3 | DOC-DEV-001 | Document Workflow | Numbering | Implement quotation number generation | QTN-006; BIZ-006 | P0 | 1 day | BIZ-DEV-002; QTN-DEV-005 | Not Started | Increment quotation_next_number
Sprint 3 | DOC-DEV-002 | Document Workflow | Numbering | Implement invoice number generation | INV-006; BIZ-006 | P0 | 1 day | BIZ-DEV-002; INV-DEV-005 | Not Started | Increment invoice_next_number
Sprint 3 | DOC-DEV-003 | Document Workflow | Quotations | Implement convert quotation to invoice | QTN-010; INV-010 | P0 | 1.5 days | QTN-DEV-005; INV-DEV-005 | Not Started | Copy customer, items, notes, totals
Sprint 3 | DOC-DEV-004 | Document Workflow | Invoices | Implement invoice duplicate | INV-009 | P1 | 0.5 day | INV-DEV-005 | Not Started | Create new invoice from existing
Sprint 3 | PAY-DEV-001 | Document Workflow | Payments | Build Record Payment dialog | PAY-001; PAY-002; PAY-003; PAY-004; PAY-005 | P0 | 1 day | INV-DEV-006 | Not Started | Full and partial payment
Sprint 3 | PAY-DEV-002 | Document Workflow | Payments | Implement PaymentRepository | PAY-001; PAY-002; PAY-003; PAY-004; PAY-006 | P0 | 1 day | DB-DEV-005 | Not Started | Create payment records
Sprint 3 | PAY-DEV-003 | Document Workflow | Payments | Update invoice after payment | PAY-006; INV-008 | P0 | 1 day | PAY-DEV-002; INV-DEV-005 | Not Started | Update amount_paid, balance_due, status
Sprint 3 | PAY-DEV-004 | Document Workflow | Payments | Implement mark as paid flow | PAY-001 | P0 | 0.5 day | PAY-DEV-001; PAY-DEV-003 | Not Started | Prefill outstanding amount
Sprint 3 | PAY-DEV-005 | Document Workflow | Payments | Implement mark as partial flow | PAY-002 | P0 | 0.5 day | PAY-DEV-001; PAY-DEV-003 | Not Started | User enters partial amount
Sprint 3 | REM-DEV-001 | Document Workflow | Reminders | Implement due state calculation | REM-001; REM-002 | P0 | 1 day | INV-DEV-005; PAY-DEV-003 | Not Started | due_soon, due_today, overdue
Sprint 3 | HOME-DEV-002 | Document Workflow | Dashboard | Build dashboard summary query | HOME-001 | P0 | 1 day | INV-DEV-005; PAY-DEV-003; REM-DEV-001 | Not Started | Unpaid, overdue, due this week
Sprint 3 | HOME-DEV-003 | Document Workflow | Dashboard | Show recent invoices and quotations | HOME-002; HOME-003 | P1 | 0.5 day | QTN-DEV-005; INV-DEV-005 | Not Started | Recent activity blocks
Sprint 3 | HOME-DEV-004 | Document Workflow | Dashboard | Implement quick actions | HOME-004 | P0 | 0.5 day | HOME-DEV-001 | Not Started | New customer, quotation, invoice
Sprint 4 | PDF-DEV-001 | PDF & Sharing | PDF | Create base PDF layout engine | PDF-001; PDF-002 | P0 | 1.5 days | QTN-DEV-005; INV-DEV-005; BIZ-DEV-002 | Not Started | Use Flutter pdf package
Sprint 4 | PDF-DEV-002 | PDF & Sharing | PDF | Implement quotation PDF template | PDF-001; PDF-003; PDF-004 | P0 | 1.5 days | PDF-DEV-001 | Not Started | Professional layout
Sprint 4 | PDF-DEV-003 | PDF & Sharing | PDF | Implement invoice PDF template | PDF-002; PDF-003; PDF-004 | P0 | 1.5 days | PDF-DEV-001 | Not Started | Include payment instructions
Sprint 4 | PDF-DEV-004 | PDF & Sharing | PDF | Implement logo support in PDF | PDF-003; BIZ-003 | P1 | 1 day | PDF-DEV-001; SET-DEV-002 | Not Started | Fetch from Supabase Storage
Sprint 4 | PDF-DEV-005 | PDF & Sharing | PDF | Add PDF preview screen | PDF-001; PDF-002 | P1 | 1 day | PDF-DEV-002; PDF-DEV-003 | Not Started | Optional but useful
Sprint 4 | SHR-DEV-001 | PDF & Sharing | Sharing | Implement system share sheet for PDFs | SHR-001; QTN-014; INV-014 | P0 | 1 day | PDF-DEV-002; PDF-DEV-003 | Not Started | Use share_plus
Sprint 4 | SHR-DEV-002 | PDF & Sharing | Sharing | Implement WhatsApp share flow | SHR-002; QTN-015; INV-015 | P1 | 1 day | SHR-DEV-001 | Not Started | Use system share/deep link fallback
Sprint 4 | SHR-DEV-003 | PDF & Sharing | Sharing | Implement open WhatsApp chat action | SHR-003; CUS-007 | P1 | 0.5 day | CUS-DEV-003 | Not Started | Use phone/WhatsApp number
Sprint 4 | SHR-DEV-004 | PDF & Sharing | Sharing | Implement copy quotation message | SHR-004 | P1 | 0.5 day | QTN-DEV-006 | Not Started | Use template string
Sprint 4 | SHR-DEV-005 | PDF & Sharing | Sharing | Implement copy invoice message | SHR-005 | P1 | 0.5 day | INV-DEV-006 | Not Started | Use template string
Sprint 4 | REM-DEV-002 | PDF & Sharing | Sharing | Implement copy reminder message | REM-004; REM-005 | P1 | 0.5 day | INV-DEV-006; REM-DEV-001 | Not Started | For overdue follow-up
Sprint 5 | FCM-DEV-001 | Push Reminders | Firebase | Create Firebase project and enable FCM | REM-003 | P0 | 0.5 day |  | Not Started | Android app config
Sprint 5 | FCM-DEV-002 | Push Reminders | Flutter | Add Firebase packages to Flutter | REM-003 | P0 | 0.5 day | FCM-DEV-001 | Not Started | firebase_core, firebase_messaging
Sprint 5 | FCM-DEV-003 | Push Reminders | Flutter | Request notification permission | REM-003 | P0 | 0.5 day | FCM-DEV-002 | Not Started | Android 13+ permission handling
Sprint 5 | FCM-DEV-004 | Push Reminders | Flutter | Get and save FCM token | REM-003 | P0 | 1 day | FCM-DEV-002; DB-DEV-006 | Not Started | Save into user_devices
Sprint 5 | FCM-DEV-005 | Push Reminders | Flutter | Handle FCM token refresh | REM-003 | P0 | 0.5 day | FCM-DEV-004 | Not Started | Update user_devices
Sprint 5 | FCM-DEV-006 | Push Reminders | Flutter | Handle notification tap | REM-003; REM-006 | P1 | 1 day | FCM-DEV-002; INV-DEV-006 | Not Started | Open invoice detail if invoice_id included
Sprint 5 | FCM-DEV-007 | Push Reminders | Supabase Edge Function | Create process-reminders Edge Function | REM-003; REM-004; REM-006 | P0 | 2 days | DB-DEV-006; INV-DEV-005; PAY-DEV-003 | Not Started | Check due invoices and send FCM
Sprint 5 | FCM-DEV-008 | Push Reminders | Supabase Edge Function | Add Firebase service account secrets | REM-003 | P0 | 0.5 day | FCM-DEV-007 | Not Started | Never store server key in Flutter
Sprint 5 | FCM-DEV-009 | Push Reminders | Supabase Edge Function | Implement duplicate reminder prevention | REM-008 | P0 | 1 day | FCM-DEV-007 | Not Started | Check reminder_logs before sending
Sprint 5 | FCM-DEV-010 | Push Reminders | Supabase Edge Function | Handle invalid FCM tokens | REM-003 | P1 | 0.5 day | FCM-DEV-007 | Not Started | Mark user_devices.is_active = false
Sprint 5 | FCM-DEV-011 | Push Reminders | Cron | Setup external cron to call Edge Function | REM-003 | P0 | 0.5 day | FCM-DEV-007 | Not Started | Cloudflare Cron/Vercel Cron/GitHub Actions/EasyCron
Sprint 5 | FCM-DEV-012 | Push Reminders | Reminders | Build reminder settings screen | SET-002; SET-005; REM-007 | P1 | 1 day | DB-DEV-006 | Not Started | Default before/on/after due settings
Sprint 5 | FCM-DEV-013 | Push Reminders | Reminders | Build reminder view or home reminder section | REM-001; REM-002; REM-006 | P0 | 1 day | REM-DEV-001; HOME-DEV-002 | Not Started | Due soon, due today, overdue
Sprint 6 | SET-DEV-001 | Settings & Polish | Settings | Build Settings main screen | SET-001; SET-002; SET-003; SET-004; SET-005; AUTH-004 | P0 | 1 day | HOME-DEV-001 | Not Started | Settings hub
Sprint 6 | SET-DEV-002 | Settings & Polish | Business Profile | Build business profile settings screen | BIZ-002; BIZ-003; BIZ-004; BIZ-005; BIZ-007 | P0 | 1.5 days | BIZ-DEV-002; SET-DEV-001 | Not Started | Include logo upload
Sprint 6 | SET-DEV-003 | Settings & Polish | Storage | Setup Supabase Storage for logos | BIZ-003 | P1 | 1 day | SETUP-006; SET-DEV-002 | Not Started | Private/user-owned logo bucket
Sprint 6 | SET-DEV-004 | Settings & Polish | Settings | Build numbering settings screen | BIZ-006; SET-003 | P1 | 1 day | SET-DEV-001 | Not Started | Quotation/invoice prefixes
Sprint 6 | SET-DEV-005 | Settings & Polish | Settings | Build default notes/payment instructions settings | BIZ-004; BIZ-005; SET-004 | P1 | 1 day | SET-DEV-001 | Not Started | Can combine with business settings
Sprint 6 | UI-DEV-001 | Settings & Polish | UI Polish | Design empty states for major screens |  | P1 | 1 day | CUS-DEV-001; QTN-DEV-001; INV-DEV-001 | Not Started | Guide user to first action
Sprint 6 | UI-DEV-002 | Settings & Polish | UI Polish | Add loading and error states |  | P0 | 1.5 days | All core screens | Not Started | Essential for production feel
Sprint 6 | UI-DEV-003 | Settings & Polish | UI Polish | Improve status badges and color system |  | P1 | 0.5 day | QTN-DEV-006; INV-DEV-006 | Not Started | Draft, sent, paid, overdue etc.
Sprint 6 | UI-DEV-004 | Settings & Polish | UI Polish | Add onboarding checklist |  | P1 | 1 day | BIZ-DEV-001; CUS-DEV-001; QTN-DEV-001; INV-DEV-001 | Not Started | Improves activation
Sprint 6 | QA-DEV-001 | Settings & Polish | QA | Test auth flows |  | P0 | 0.5 day | AUTH-DEV-001 to AUTH-DEV-006 | Not Started | Register, login, forgot password, logout
Sprint 6 | QA-DEV-002 | Settings & Polish | QA | Test customer CRUD |  | P0 | 0.5 day | CUS-DEV-001 to CUS-DEV-005 | Not Started | Create/edit/archive/search
Sprint 6 | QA-DEV-003 | Settings & Polish | QA | Test quotation workflow |  | P0 | 1 day | QTN-DEV-001 to QTN-DEV-008 | Not Started | Create, edit, duplicate, convert
Sprint 6 | QA-DEV-004 | Settings & Polish | QA | Test invoice and payment workflow |  | P0 | 1 day | INV-DEV-001 to PAY-DEV-005 | Not Started | Partial/full payment and balance
Sprint 6 | QA-DEV-005 | Settings & Polish | QA | Test PDF and sharing workflow |  | P0 | 1 day | PDF-DEV-001 to SHR-DEV-005 | Not Started | Generate and share PDF
Sprint 6 | QA-DEV-006 | Settings & Polish | QA | Test FCM reminder workflow |  | P0 | 1 day | FCM-DEV-001 to FCM-DEV-013 | Not Started | Use test invoice due dates
Sprint 6 | QA-DEV-007 | Settings & Polish | QA | Test RLS data isolation |  | P0 | 1 day | DB-DEV-007 to DB-DEV-011 | Not Started | Critical security check
Sprint 6 | QA-DEV-008 | Settings & Polish | QA | Fix critical bugs before beta |  | P0 | 2 days | QA-DEV-001 to QA-DEV-007 | Not Started | Bug fixing buffer
Sprint 7 | BETA-001 | Beta Release | Release Prep | Add app icon and splash branding |  | P1 | 0.5 day | UI-DEV-001 | Not Started | Basic branding
Sprint 7 | BETA-002 | Beta Release | Release Prep | Prepare privacy policy |  | P0 | 0.5 day |  | Not Started | Required for Play Store
Sprint 7 | BETA-003 | Beta Release | Release Prep | Prepare terms of use |  | P1 | 0.5 day |  | Not Started | Recommended
Sprint 7 | BETA-004 | Beta Release | Release Prep | Create landing page |  | P1 | 1 day |  | Not Started | Carrd/Framer/Next.js
Sprint 7 | BETA-005 | Beta Release | Analytics | Add analytics events |  | P1 | 1 day | Core workflows | Not Started | Track profile created, invoice created, PDF shared
Sprint 7 | BETA-006 | Beta Release | Monitoring | Add crash reporting |  | P1 | 1 day |  | Not Started | Sentry recommended
Sprint 7 | BETA-007 | Beta Release | Release Prep | Prepare Android release build |  | P0 | 1 day | All P0 features | Not Started | Keystore, build config
Sprint 7 | BETA-008 | Beta Release | Release Prep | Internal testing release |  | P0 | 1 day | BETA-007 | Not Started | Test on real devices
Sprint 7 | BETA-009 | Beta Release | User Testing | Recruit 5 to 10 beta users |  | P0 | 2 days | BETA-008 | Not Started | Freelancers/small business owners
Sprint 7 | BETA-010 | Beta Release | User Testing | Collect beta feedback |  | P0 | 3 days | BETA-009 | Not Started | Focus on invoice/PDF/share/reminder flow
Sprint 7 | BETA-011 | Beta Release | User Testing | Fix beta feedback issues |  | P0 | 3 days | BETA-010 | Not Started | Prioritize blocking UX problems
Sprint 7 | BETA-012 | Beta Release | Release Prep | Prepare Play Store listing |  | P0 | 1 day | BETA-011 | Not Started | Screenshots, description, category
Sprint 7 | BETA-013 | Beta Release | Release Prep | Submit to Play Store |  | P0 | 0.5 day | BETA-012 | Not Started | Production or closed testing first
V2 Sprint 1 | V2-CAT-001 | V2 Enhancement | Saved Items | Create saved_items table | CAT-001 | P1 | 0.5 day |  | Not Started | If not created in V1 migration
V2 Sprint 1 | V2-CAT-002 | V2 Enhancement | Saved Items | Build Saved Items List screen | CAT-001 | P1 | 1 day | V2-CAT-001 | Not Started | Service catalog
V2 Sprint 1 | V2-CAT-003 | V2 Enhancement | Saved Items | Build Create/Edit Saved Item form | CAT-003 | P1 | 1 day | V2-CAT-002 | Not Started | Item name, description, unit price
V2 Sprint 1 | V2-CAT-004 | V2 Enhancement | Saved Items | Insert saved item into quotation/invoice | CAT-002 | P1 | 1.5 days | V2-CAT-003; QTN-DEV-002; INV-DEV-002 | Not Started | Reduces repeated data entry
V2 Sprint 1 | V2-CUS-001 | V2 Enhancement | Customers | Enhance customer history summary | CUS-008 | P1 | 1.5 days | PAY-DEV-003; CUS-DEV-003 | Not Started | Total invoiced, paid, unpaid
V2 Sprint 1 | V2-PAY-001 | V2 Enhancement | Payments | Build payment history list | PAY-007 | P1 | 1 day | PAY-DEV-002 | Not Started | Inside invoice detail
V2 Sprint 1 | V2-EXP-001 | V2 Enhancement | Export | Build export screen | SET-006; EXP-001; EXP-002; EXP-003; EXP-004 | P1 | 1.5 days | SET-DEV-001 | Not Started | CSV first
V2 Sprint 1 | V2-EXP-002 | V2 Enhancement | Export | Implement CSV export for customers | EXP-001 | P1 | 1 day | V2-EXP-001 | Not Started
V2 Sprint 1 | V2-EXP-003 | V2 Enhancement | Export | Implement CSV export for invoices | EXP-002 | P1 | 1 day | V2-EXP-001 | Not Started
V2 Sprint 1 | V2-EXP-004 | V2 Enhancement | Export | Implement CSV export for payments | EXP-003 | P1 | 1 day | V2-EXP-001 | Not Started
V2 Sprint 2 | V2-PDF-001 | V2 Enhancement | PDF | Design second PDF template | PDF-005 | P1 | 2 days | PDF-DEV-001 | Not Started | Formal business style
V2 Sprint 2 | V2-PDF-002 | V2 Enhancement | PDF | Add PDF template selector | PDF-005 | P1 | 1 day | V2-PDF-001 | Not Started | Save user preference
V2 Sprint 2 | V2-PDF-003 | V2 Enhancement | PDF | Add accent color selection | PDF-006 | P2 | 1 day | V2-PDF-002 | Not Started | Optional
V2 Sprint 2 | V2-REM-001 | V2 Enhancement | Reminders | Add customizable reminder schedule | REM-007 | P1 | 1.5 days | FCM-DEV-007; FCM-DEV-012 | Not Started | User-defined reminder days
V2 Sprint 2 | V2-REM-002 | V2 Enhancement | Reminders | Add reminder history UI | REM-008 | P2 | 1 day | FCM-DEV-009 | Not Started | Show sent/failed logs
V2 Sprint 2 | V2-REM-003 | V2 Enhancement | Reminders | Add snooze reminder | REM-009 | P2 | 1.5 days | V2-REM-002 | Not Started | Useful but not urgent
V2 Sprint 2 | V2-SHR-001 | V2 Enhancement | Sharing | Build message template settings | SHR-006 | P1 | 1.5 days | SET-DEV-001 | Not Started | Quotation, invoice, reminder templates
V2 Sprint 2 | V2-SHR-002 | V2 Enhancement | Sharing | Implement one-tap reminder share flow | SHR-007 | P2 | 1 day | V2-SHR-001; REM-DEV-002 | Not Started | Improve follow-up speed
V2 Sprint 3 | V2-ARC-001 | V2 Enhancement | Archive | Create archive manager screen | SET-007; CUS-009; INV-017 | P2 | 1.5 days | CUS-DEV-005; INV-DEV-005 | Not Started | View archived records
V2 Sprint 3 | V2-ARC-002 | V2 Enhancement | Archive | Implement restore customer | CUS-009 | P1 | 0.5 day | V2-ARC-001 | Not Started
V2 Sprint 3 | V2-ARC-003 | V2 Enhancement | Archive | Implement restore invoice | INV-017 | P1 | 0.5 day | V2-ARC-001 | Not Started
V2 Sprint 3 | V2-ACT-001 | V2 Enhancement | Activity Logs | Create document_activity_logs table | QTN-016; INV-016 | P2 | 0.5 day |  | Not Started | If not created earlier
V2 Sprint 3 | V2-ACT-002 | V2 Enhancement | Activity Logs | Log quotation/invoice key events | QTN-016; INV-016 | P2 | 1.5 days | V2-ACT-001 | Not Started | Created, updated, shared, paid
V2 Sprint 3 | V2-ACT-003 | V2 Enhancement | Activity Logs | Show activity timeline in detail screens | QTN-016; INV-016 | P2 | 1.5 days | V2-ACT-002 | Not Started | Embedded in detail pages
V2 Sprint 3 | V2-HOME-001 | V2 Enhancement | Dashboard | Add monthly insights | HOME-005 | P1 | 1.5 days | HOME-DEV-002 | Not Started | Monthly invoiced and collected
V2 Sprint 3 | V2-HOME-002 | V2 Enhancement | Dashboard | Add top customers card | HOME-006 | P2 | 1 day | V2-CUS-001 | Not Started | Top customers by invoice total